## Sheet1
| Tasks Name | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
Store Page | Header |  |  |  | Trung
| Header - Nav bar | 2024-01-19 | 2024-01-20
| Header - Shopping Cart | 2024-01-24 | 2024-01-26
Shopping Cart
Shopping Cart - Product List
Shopping Cart - Increase/Decrease Quantity Buttons
Shopping Cart - Total
Shopping Cart - Purchase Button
Body
| Body - Banner | 2024-01-22 | 2024-01-22
| Body - Product List | 2024-01-23 | 2024-01-24
| Body - Product Filter | 2024-01-23 | 2024-01-24
Product List
| Product List - Product Card | 2024-01-24 | 2024-01-26
| Product List - Add to Cart Button | 2024-01-24 | 2024-01-26
Admin Page | Header |  |  |  | Quân
Body
Product API: https://65a5f64474cf4207b4ef0e03.mockapi.io/PhoneProducts/
Cart API: https://65a9efbb081bd82e1d95bdd2.mockapi.io/cart